## POA&M
Control identifiers follow NIST SP 800-53 conventions and should be verified against the current revision, because identifiers and control structure have changed between revisions.
ID | Weakness | Control | Remediation | Owner | Due | Status | Risk Rating
POA&M-01 | Boundary segmentation was tested once and has not been re-tested, although the rule set has changed since | SC-7 | Re-run the both-direction boundary test and record the result; add it to recurring monthly verification | [System Owner] | 2026-09-01 | Open | High
POA&M-02 | Firewall configuration is not under version control; change evidence depends on manual entries | SC-7, CM-3 | Export the firewall configuration to the Git repository on a schedule | [System Owner] | 2026-10-01 | Open | High
POA&M-03 | Container application logs are not collected; application-layer attacks produced no alerts | AU-2 | Configure the log agent to read container logs; verify by repeating one attack and confirming an alert | [System Owner] | 2026-09-01 | Open | High
POA&M-04 | Directory enumeration is not detectable with current rules; the activity is indistinguishable from normal authenticated queries | AU-6 | Accepted as not signature-detectable. Investigate behavioural baselining as a longer-term option | [System Owner] | 2027-02-01 | Open | Medium
POA&M-05 | Restore testing has a single data point; no operating trend exists | CP-10 | Perform and log a monthly restore test; re-assess after three months | [System Owner] | 2026-11-01 | Open | Medium
POA&M-06 | Audit record review is performed ad hoc rather than on a defined schedule | AU-6 | Define and follow a weekly alert queue review; record each review with date and outcome | [System Owner] | 2026-09-01 | Open | Medium
POA&M-07 | Only 15 controls of the Moderate baseline have been assessed | CA-2 | Assess a further 15 controls, prioritising the AC and IA families | [System Owner] | 2027-02-01 | Open | Medium
POA&M-08 | File integrity monitoring is not configured for scheduled-task directories, privilege configuration directories, or user key files | SI-7, AU-2 | Enable file integrity monitoring on those paths; verify by making a test change and confirming an alert | [System Owner] | 2026-09-01 | Open | High
POA&M-09 | Windows patching automation has been written and syntax-checked but never executed against domain controllers | SI-2 | Execute in check mode, then against the secondary controller alone, before scheduling | [System Owner] | 2026-10-01 | Open | High
POA&M-10 | No defined procedure exists for certificate revocation or CA key compromise | SC-12 | Write and test a revocation runbook covering both a single certificate and a CA key compromise | [System Owner] | 2026-11-01 | Open | High

## Risk Register
Control identifiers follow NIST SP 800-53 conventions and should be verified against the current revision, because identifiers and control structure have changed between revisions.
ID | Risk and consequence | Likelihood | Impact | Score | Response | Mitigation | Decider | Review Date | Status
R-01 | The hypervisor hosting every component is a personal general-purpose machine outside the boundary; therefore its compromise or failure results in the compromise or loss of every component of GSS-1 regardless of any internal control | 3 | 5 | 15 | Accept, with mitigation | Backups held on separate media, so host failure costs availability but not data; full-disk encryption on the host | [System Owner] | 2026-11-01 | Active
R-02 | A monitoring suppression rule for the authorised testing host reduces alerting from that source; therefore an attacker who compromises it operates from a partial blind spot, as demonstrated during internal testing | 2 | 4 | 8 | Accept, deliberately | Exception is narrow, limited to one source address, commented, and version-controlled; host is powered off when not in use | [System Owner] | 2026-11-01 | Active
R-03 | Firewall rule changes are recorded only by manual log entries; therefore a rule added and forgotten can persist unnoticed and widen the attack surface with no record, as occurred with a temporary rule during testing | 4 | 3 | 12 | Mitigate | Tracked as POA&M-02 | [System Owner] | 2026-10-01 | Active
R-04 | One person holds all knowledge and all access; therefore absence, illness, or credential loss leaves nobody able to operate or recover the system | 2 | 4 | 8 | Accept | Runbooks documented rather than remembered; credentials in a password manager with recovery configured | [System Owner] | 2027-02-01 | Active
R-05 | Several attack techniques used during authorised testing are not detectable by signature because they are indistinguishable from normal authenticated activity; therefore an intruder using them would not be detected by current monitoring | 3 | 4 | 12 | Accept, characterised | Documented as a known limitation with the reasoning; behavioural baselining identified as the only viable approach and tracked as POA&M-04 | [System Owner] | 2027-02-01 | Active

## Closed Items
Control identifiers follow NIST SP 800-53 conventions and should be verified against the current revision, because identifiers and control structure have changed between revisions.
ID | Weakness | Control | Remediation | Owner | Due | Status | Risk Rating | Date Closed | Closing Evidence
Instruction | Move completed POA&M items to this worksheet with their original content, closure date, and objective closing evidence. Items are moved here rather than deleted. |  |  |  |  | Closed

## Control Status
Control identifiers follow NIST SP 800-53 conventions and should be verified against the current revision, because identifiers and control structure have changed between revisions.
Control | Control Name | Grade | Grade | Count
AC-2 | Account Management | Implemented | Implemented | 7
AC-8 | System Use Notification | Implemented | Partially Implemented | 8
AC-17 | Remote Access | Partially Implemented | Planned | 0
AU-2 | Event Logging | Partially Implemented | Not Implemented | 0
AU-6 | Audit Record Review | Partially Implemented | Not Applicable | 0
CA-8 | Penetration Testing | Implemented
CM-3 | Configuration Change Control | Partially Implemented
CP-9 | System Backup | Implemented
CP-10 | System Recovery | Implemented
IA-2 | Identification and Authentication | Implemented
IA-5 | Authenticator Management | Partially Implemented
RA-5 | Vulnerability Monitoring and Scanning | Implemented
SC-7 | Boundary Protection | Partially Implemented
SC-12 | Cryptographic Key Establishment and Management | Partially Implemented
SI-2 | Flaw Remediation | Partially Implemented

## Instructions
Control identifiers follow NIST SP 800-53 conventions and should be verified against the current revision, because identifiers and control structure have changed between revisions.
Workbook Maintenance | Guidance
Assessment date | 2026-08-01. All due dates and review dates are calculated from this common assessment date.
POA&M workflow | Update Status as work proceeds. Use Open, In Progress, or Closed. When an item is complete, move the entire row to Closed Items and add Date Closed and Closing Evidence. Do not delete closed items.
Weakness | Describe the observed deficiency or limitation. Keep the statement factual and specific enough that closure can be tested.
Control | Use the NIST SP 800-53 control identifier associated with the weakness. Multiple controls may be listed when the issue crosses control boundaries.
Remediation | State the action that will correct or formally resolve the weakness, including the verification step.
Owner | Name the individual accountable for completing the action. The current package uses [System Owner].
Due | Use an actual target date. Overdue open items are highlighted automatically.
Risk Rating | Calculated from the linked control and weakness category in the POA&M sheet. It supports prioritisation but does not replace the risk register score.
Risk Register Score | Computed as likelihood multiplied by impact. The score orders risks for comparison and is not a prediction.
Evidence | Closing evidence should be objective, such as a configuration export, test result, log record, screenshot reference, or signed review record.
Control Status | The chart and counts are derived from the 15 assessed controls. Grades must remain consistent with the SSP unless a new assessment is performed and documented.
Significant change | Reassess affected controls and review the authorisation if the boundary, identity architecture, firewall policy, hosting platform, or core services materially change.